## Timeline
AutoMate — 6-Month Launch Timeline (Consumer app + Dealer portal)
Month | 📱 Consumer app | 🏢 Dealer portal | 📣 Marketing / Ops
Month 1 | Prod hosting, real OTP (Twilio/SendGrid), real OAuth, Apple + Play accounts, EAS Build | Scaffold web app + dealer auth on existing API | Form LLC, Privacy/Terms, landing page + waitlist, recruit 3–5 dealers
Month 2 | Stripe Connect, push notifications, analytics + crash, AI estimate mode on CPU | Inbound requests → submit quote (core supply loop) + Stripe Connect onboarding | Content engine starts; beta recruiting
Month 3 | TestFlight / Play closed beta, funnel instrumentation, bug-fix | Bookings calendar + profile/hours/service menu — dealers use it live in beta | Closed beta: ~20–50 users + pilot dealers (real two-sided test)
Month 4 | Accessibility, QA matrix, security review, ASO + data-safety forms | Analytics + payout testing + polish; harden | Referral mechanics live; PR list; open beta
Month 5 | Submit both stores; soft launch (budget 1–2 review cycles) | Onboard dealers for soft launch; portal stable | NoVA soft launch; dealer co-promo; Product Hunt prep
Month 6 | Public launch; iterate on real data | Dealers self-serve via portal at launch | Launch push (PH, local PR, groups, small paid test); traction story
Go/no-go gates: M1 real signup→OTP→login · M2 test-mode booking pays + dealer submits a portal quote · M3 ≥1 real user↔dealer booking · M5 both store approvals · M6 publicly downloadable + first organic cohort

## Budget
AutoMate — 6-Month Budget (Bootstrapped, < $25k)
Item | Low (USD) | High (USD)
Apple Developer ($99) + Google Play ($25) | 125 | 125
Hosting — DB + API + image storage + AI (CPU) | 750 | 750
Portal web hosting (Vercel/Netlify) | 0 | 120
SMS / email OTP (Twilio + SendGrid) | 300 | 300
Domain, email, legal-docs tooling | 300 | 300
Legal review (entity + ToS/privacy + marketplace/payout terms) | 2000 | 3500
Maps API (or $0 on OpenStreetMap) | 0 | 300
Design / store + portal assets | 600 | 600
Paid marketing test (post beta) | 1500 | 3000
Optional contractor sprint (parallelize portal) | 3000 | 6000
Contingency | 2000 | 2000
TOTAL RANGE
Under $25k even with the contractor sprint. Dev-partner equity (not cash) is the linchpin. Figures are planning estimates, not quotes.

## Risks
AutoMate — Top Risks & Mitigations
Risk | Mitigation
Two-sided liquidity (empty app) | Portal makes dealers self-serve; lock 2–3 dealers before launch; concierge early quotes
Portal stretches one dev too thin | MVP scope + concierge fallback + optional contractor sprint; portal may trail consumer by weeks
Store rejection (marketplace + insurance/photo data) | Data-safety forms, account deletion, disclaimers; budget 1–2 review cycles
Payout / marketplace compliance | Stripe Connect handles KYC; lawyer reviews marketplace + payout terms
AI accuracy expectations | Ship as transparent estimate; disclose assumptions (already on Compare tab); train model post-raise
Prototype → production (Expo SDK, real builds) | Do EAS Build in Month 1, not Month 5

## KPIs
AutoMate — KPIs to Track (from Month 3)
Side | Metric | Why it matters
Consumer | Signups | Top-of-funnel demand
Consumer | Activation (completed estimate) | Did they reach the aha moment
Consumer | Quote → booking conversion | Core marketplace conversion
Consumer | Bookings | Real transactions
Consumer | D7 / D30 retention | Stickiness
Consumer | Referral rate | Organic growth loop (points)
Consumer | Crash-free rate | Quality / store rating health
Dealer | Active dealers | Supply-side liquidity
Dealer | Avg response time | Quote speed = user experience
Dealer | Quote-acceptance rate | Pricing competitiveness
Dealer | Bookings fulfilled | Supply reliability
Dealer | GMV (gross marketplace value) | Revenue base / take-rate input